## Overview
DANAMECO SHOP
I. Project description | - Xây dựng web bán hàng thương mại điện tử và app bán hàng cho công ty Danameco. - Dự án có tên: Danameco Shop.
Product Owner: Lê Đình Tuyên
Scrum master: Nguyễn Quang Phúc Đạt
II. Project estimation
Total effort: | 945
Details:
III. Project plan | Ngày bắt đầu |  | 2020-10-05
| Ngày kết thúc |  | 2020-11-29

## Estimation
DANAMECO SHOP ESTIMATION
Project name |  | Danameco Shop |  | Project ID | 43K22T09
Project manager |  | 43K22T09 |  | Sponsor | Cao Thi Nham
Start date |  | 2020-10-05 |  | End date | 2020-11-29
ID | Task name | Phase | Description | Estimation Effort | Actual effort
1 | [Website - Users] Design Home Page | Sprint 1 |  | 10
2 | [Website - Users] Build Home Page | Sprint 1 |  | 10
3 | [Website - Users] Test Home Page | Sprint 1 |  | 5
4 | [Website - Users] Design About Us Page | Sprint 1 |  | 6
5 | [Website - Users] Build About Us Page | Sprint 1 |  | 6
6 | [Website - Users] Test About Us Page | Sprint 1 |  | 3
7 | [Website - Users] Design Shop Page | Sprint 1 |  | 20
8 | [Website - Users] Build Shop Page | Sprint 1 |  | 20
9 | [Website - Users] Test Shop Page | Sprint 1 |  | 10
10 | [Website - Users] Design Contact Page | Sprint 1 |  | 8
11 | [Website - Users] Build Contact Page | Sprint 1 |  | 8
12 | [Website - Users] Test Contact Page | Sprint 1 |  | 4
13 | [Website - Users] Design Cart Page | Sprint 1 |  | 8
14 | [Website - Users] Build Cart Page | Sprint 1 |  | 8
15 | [Website - Users] Test Cart Page | Sprint 1 |  | 4
16 | [Website - Users] Design Search Page | Sprint 1 |  | 8
17 | [Website - Users] Build Search Page | Sprint 1 |  | 8
18 | [Website - Users] Test Search Page | Sprint 1 |  | 4
19 | [Website - Users] Design Sign In Page | Sprint 2 |  | 6
20 | [Website - Users] Build Sign In Page | Sprint 2 |  | 6
21 | [Website - Users] Test Sign In Page | Sprint 2 |  | 3
22 | [Website - Users] Design Sign Up Page | Sprint 2 |  | 6
23 | [Website - Users] Build Sign Up Page | Sprint 2 |  | 6
24 | [Website - Users] Test Sign Up Page | Sprint 2 |  | 3
25 | [Website - Users] Design Customer Information Page | Sprint 2 |  | 4
26 | [Website - Users] Build Customer Information Page | Sprint 2 |  | 4
27 | [Website - Users] Test Customer Information Page | Sprint 2 |  | 2
28 | [Website - Users] Design Order Management Page | Sprint 2 |  | 8
29 | [Website - Users] Build Order Management Page | Sprint 2 |  | 8
30 | [Website - Users] Test Order Management Page | Sprint 2 |  | 4
31 | [Website - Admin] Design Member Management | Sprint 2 |  | 8
32 | [Website - Admin] Build Member Management | Sprint 2 |  | 8
33 | [Website - Admin] Test Member Management | Sprint 2 |  | 4
34 | [Website - Admin] Design Profile Member | Sprint 2 |  | 6
35 | [Website - Admin] Build Profile Member | Sprint 2 |  | 6
36 | [Website - Admin] Test Profile Member | Sprint 2 |  | 3
37 | [Website - Admin] Design Customer Management | Sprint 3 |  | 8
38 | [Website - Admin] Build Customer Management | Sprint 3 |  | 8
39 | [Website - Admin] Test Customer Management | Sprint 3 |  | 4
40 | [Website - Admin] Design Report Customer | Sprint 3 |  | 10
41 | [Website - Admin] Build Report Customer | Sprint 3 |  | 10
42 | [Website - Admin] Test Report Customer | Sprint 3 |  | 5
43 | [Website - Admin] Design Products Management | Sprint 3 |  | 16
44 | [Website - Admin] Build Products Management | Sprint 3 |  | 16
45 | [Website - Admin] Test Products Management | Sprint 3 |  | 8
46 | [Website - Admin] Design Add Products | Sprint 3 |  | 16
47 | [Website - Admin] Build Add Products | Sprint 3 |  | 16
48 | [Website - Admin] Test Add Products | Sprint 3 |  | 8
49 | [Website - Admin] Design Customer Order | Sprint 3 |  | 8
50 | [Website - Admin] Build Customer Order | Sprint 3 |  | 8
51 | [Website - Admin] Test Customer Order | Sprint 3 |  | 4
52 | [Website - Admin] Design Report Order | Sprint 3 |  | 16
53 | [Website - Admin] Build Report Order | Sprint 3 |  | 16
54 | [Website - Admin] Test Report Order | Sprint 3 |  | 8
55 | [Website - Admin] Design Preferential Management | Sprint 4 |  | 8
56 | [Website - Admin] Build Preferential Management | Sprint 4 |  | 8
57 | [Website - Admin] Test Preferential Management | Sprint 4 |  | 4
58 | [Website - Admin] Design Warehouse Report | Sprint 4 |  | 10
59 | [Website - Admin] Build Warehouse Report | Sprint 4 |  | 10
60 | [Website - Admin] Test Warehouse Report | Sprint 4 |  | 5
61 | [Website - Admin] Design Setting | Sprint 4 |  | 16
62 | [Website - Admin] Build Setting | Sprint 4 |  | 16
63 | [Website - Admin] Test Setting | Sprint 4 |  | 8
64 | [App - Users] Design Home | Sprint 4 |  | 6
65 | [App - Users] Build Home | Sprint 4 |  | 6
66 | [App - Users] Test Home | Sprint 4 |  | 3
67 | [App - Users] Design Shop | Sprint 4 |  | 10
68 | [App - Users] Build Shop | Sprint 4 |  | 10
69 | [App - Users] Test Shop | Sprint 4 |  | 5
70 | [App - Users] Design Messenger | Sprint 4 |  | 6
71 | [App - Users] Build Messenger | Sprint 4 |  | 6
72 | [App - Users] Test Messenger | Sprint 4 |  | 3
73 | [App - Users] Design Account | Sprint 5 |  | 6
74 | [App - Users] Build Account | Sprint 5 |  | 6
75 | [App - Users] Test Account | Sprint 5 |  | 3
76 | [App - Users] Design Sign in | Sprint 5 |  | 6
77 | [App - Users] Build Sign in | Sprint 5 |  | 6
78 | [App - Users] Test Sign in | Sprint 5 |  | 3
79 | [App - Users] Design Sign up | Sprint 5 |  | 6
80 | [App - Users] Build Sign up | Sprint 5 |  | 6
81 | [App - Users] Test Sign up | Sprint 5 |  | 3
82 | [App - Users] Design Edit Profile | Sprint 5 |  | 6
83 | [App - Users] Build Edit Profile | Sprint 5 |  | 6
84 | [App - Users] Test Edit Profile | Sprint 5 |  | 3
85 | [App - Users] Design Reset Password | Sprint 5 |  | 6
86 | [App - Users] Build Reset Password | Sprint 5 |  | 6
87 | [App - Users] Test Reset Password | Sprint 5 |  | 3
88 | [App - Users] Design Order Management | Sprint 5 |  | 8
89 | [App - Users] Build Order Management | Sprint 5 |  | 8
90 | [App - Users] Test Order Management | Sprint 5 |  | 4
91 | [App - Users] Design Reset Password Level 2 | Sprint 6 |  | 6
92 | [App - Users] Build Reset Password Level 2 | Sprint 6 |  | 6
93 | [App - Users] Test Reset Password Level 2 | Sprint 6 |  | 3
94 | [App - Users] Design Inform | Sprint 6 |  | 6
95 | [App - Users] Build Inform | Sprint 6 |  | 6
96 | [App - Users] Test Inform | Sprint 6 |  | 3
97 | [App - Users] Design About us | Sprint 6 |  | 6
98 | [App - Users] Build About us | Sprint 6 |  | 6
99 | [App - Users] Test About us | Sprint 6 |  | 3
100 | [App - Users] Design Cart | Sprint 6 |  | 8
101 | [App - Users] Build Cart | Sprint 6 |  | 8
102 | [App - Users] Test Cart | Sprint 6 |  | 4
103 | [App - Users] Design Pay | Sprint 6 |  | 8
104 | [App - Users] Build Pay | Sprint 6 |  | 8
105 | [App - Users] Test Pay | Sprint 6 |  | 4
106 | [App - Users] Design Search | Sprint 6 |  | 8
107 | [App - Users] Build Search | Sprint 6 |  | 8
108 | [App - Users] Test Search | Sprint 6 |  | 4
109 | [App - Admin] Design Member Management | Sprint 7 |  | 8
110 | [App - Admin] Build Member Management | Sprint 7 |  | 8
111 | [App - Admin] Test Member Management | Sprint 7 |  | 4
112 | [App - Admin] Design Shop Management | Sprint 7 |  | 16
113 | [App - Admin] Build Shop Management | Sprint 7 |  | 16
114 | [App - Admin] Test Shop Management | Sprint 7 |  | 8
115 | [App - Admin] Design List Products Management | Sprint 7 |  | 8
116 | [App - Admin] Build List Products Management | Sprint 7 |  | 8
117 | [App - Admin] Test List Products Management | Sprint 7 |  | 4
118 | [App - Admin] Design List Customer Management | Sprint 7 |  | 8
119 | [App - Admin] Build List Customer Management | Sprint 7 |  | 8
120 | [App - Admin] Test List Customer Management | Sprint 7 |  | 4
121 | [App - Admin] Design Customer Notification Management | Sprint 7 |  | 6
122 | [App - Admin] Build Customer Notification Management | Sprint 7 |  | 6
123 | [App - Admin] Test Customer Notification Management | Sprint 7 |  | 3
124 | [App - Admin] Design Manage Customer Orders | Sprint 7 |  | 8
125 | [App - Admin] Build Manage Customer Orders | Sprint 7 |  | 8
126 | [App - Admin] Test Manage Customer Orders | Sprint 7 |  | 4
127 | [App - Admin] Design Messenger Mangement | Sprint 8 |  | 6
128 | [App - Admin] Build Messenger Mangement | Sprint 8 |  | 6
129 | [App - Admin] Test Messenger Mangement | Sprint 8 |  | 3
130 | [App - Admin] Design Payment Settings | Sprint 8 |  | 4
131 | [App - Admin] Build Payment Settings | Sprint 8 |  | 4
132 | [App - Admin] Test Payment Settings | Sprint 8 |  | 2
133 | [App - Admin] Design Shipping Settings | Sprint 8 |  | 6
134 | [App - Admin] Build Shipping Settings | Sprint 8 |  | 6
135 | [App - Admin] Test Shipping Settings | Sprint 8 |  | 3
Total |  |  |  | 945

## Plan
DANAMECO SHOP PLAN
| Project name | Danameco Shop |  | Project ID | 43K22T09
| Project manager | 43K22T09 |  | Sponsor | Cao Thi Nham
| Start date | 2020-10-05 |  | End date | 2020-11-29
ID | Task name | Phase | Start date | End date | Description
| Sprint 1 |  | 2020-10-05 | 2020-10-11
1 | [Website - Users] Design Home Page | Sprint 1
2 | [Website - Users] Build Home Page | Sprint 1
3 | [Website - Users] Test Home Page | Sprint 1
4 | [Website - Users] Design About Us Page | Sprint 1
5 | [Website - Users] Build About Us Page | Sprint 1
6 | [Website - Users] Test About Us Page | Sprint 1
7 | [Website - Users] Design Shop Page | Sprint 1
8 | [Website - Users] Build Shop Page | Sprint 1
9 | [Website - Users] Test Shop Page | Sprint 1
10 | [Website - Users] Design Contact Page | Sprint 1
11 | [Website - Users] Build Contact Page | Sprint 1
12 | [Website - Users] Test Contact Page | Sprint 1
13 | [Website - Users] Design Cart Page | Sprint 1
14 | [Website - Users] Build Cart Page | Sprint 1
15 | [Website - Users] Test Cart Page | Sprint 1
16 | [Website - Users] Design Search Page | Sprint 1
17 | [Website - Users] Build Search Page | Sprint 1
18 | [Website - Users] Test Search Page | Sprint 1
| Sprint 2 |  | 2020-10-12 | 2020-10-18
19 | [Website - Users] Design Sign In Page | Sprint 2
20 | [Website - Users] Build Sign In Page | Sprint 2
21 | [Website - Users] Test Sign In Page | Sprint 2
22 | [Website - Users] Design Sign Up Page | Sprint 2
23 | [Website - Users] Build Sign Up Page | Sprint 2
24 | [Website - Users] Test Sign Up Page | Sprint 2
25 | [Website - Users] Design Customer Information Page | Sprint 2
26 | [Website - Users] Build Customer Information Page | Sprint 2
27 | [Website - Users] Test Customer Information Page | Sprint 2
28 | [Website - Users] Design Order Management Page | Sprint 2
29 | [Website - Users] Build Order Management Page | Sprint 2
30 | [Website - Users] Test Order Management Page | Sprint 2
31 | [Website - Admin] Design Member Management | Sprint 2
32 | [Website - Admin] Build Member Management | Sprint 2
33 | [Website - Admin] Test Member Management | Sprint 2
34 | [Website - Admin] Design Profile Member | Sprint 2
35 | [Website - Admin] Build Profile Member | Sprint 2
36 | [Website - Admin] Test Profile Member | Sprint 2
| Sprint 3 |  | 2020-10-19 | 2020-10-25
37 | [Website - Admin] Design Customer Management | Sprint 3
38 | [Website - Admin] Build Customer Management | Sprint 3
39 | [Website - Admin] Test Customer Management | Sprint 3
40 | [Website - Admin] Design Report Customer | Sprint 3
41 | [Website - Admin] Build Report Customer | Sprint 3
42 | [Website - Admin] Test Report Customer | Sprint 3
43 | [Website - Admin] Design Products Management | Sprint 3
44 | [Website - Admin] Build Products Management | Sprint 3
45 | [Website - Admin] Test Products Management | Sprint 3
46 | [Website - Admin] Design Add Products | Sprint 3
47 | [Website - Admin] Build Add Products | Sprint 3
48 | [Website - Admin] Test Add Products | Sprint 3
49 | [Website - Admin] Design Customer Order | Sprint 3
50 | [Website - Admin] Build Customer Order | Sprint 3
51 | [Website - Admin] Test Customer Order | Sprint 3
52 | [Website - Admin] Design Report Order | Sprint 3
53 | [Website - Admin] Build Report Order | Sprint 3
54 | [Website - Admin] Test Report Order | Sprint 3
| Sprint 4 |  | 2020-10-26 | 2020-11-01
55 | [Website - Admin] Design Preferential Management | Sprint 4
56 | [Website - Admin] Build Preferential Management | Sprint 4
57 | [Website - Admin] Test Preferential Management | Sprint 4
58 | [Website - Admin] Design Warehouse Report | Sprint 4
59 | [Website - Admin] Build Warehouse Report | Sprint 4
60 | [Website - Admin] Test Warehouse Report | Sprint 4
61 | [Website - Admin] Design Setting | Sprint 4
62 | [Website - Admin] Build Setting | Sprint 4
63 | [Website - Admin] Test Setting | Sprint 4
64 | [App - Users] Design Home | Sprint 4
65 | [App - Users] Build Home | Sprint 4
66 | [App - Users] Test Home | Sprint 4
67 | [App - Users] Design Shop | Sprint 4
68 | [App - Users] Build Shop | Sprint 4
69 | [App - Users] Test Shop | Sprint 4
70 | [App - Users] Design Messenger | Sprint 4
71 | [App - Users] Build Messenger | Sprint 4
72 | [App - Users] Test Messenger | Sprint 4
| Sprint 5 |  | 2020-11-02 | 2020-11-08
73 | [App - Users] Design Account | Sprint 5
74 | [App - Users] Build Account | Sprint 5
75 | [App - Users] Test Account | Sprint 5
76 | [App - Users] Design Sign in | Sprint 5
77 | [App - Users] Build Sign in | Sprint 5
78 | [App - Users] Test Sign in | Sprint 5
79 | [App - Users] Design Sign up | Sprint 5
80 | [App - Users] Build Sign up | Sprint 5
81 | [App - Users] Test Sign up | Sprint 5
82 | [App - Users] Design Edit Profile | Sprint 5
83 | [App - Users] Build Edit Profile | Sprint 5
84 | [App - Users] Test Edit Profile | Sprint 5
85 | [App - Users] Design Reset Password | Sprint 5
86 | [App - Users] Build Reset Password | Sprint 5
87 | [App - Users] Test Reset Password | Sprint 5
88 | [App - Users] Design Order Management | Sprint 5
89 | [App - Users] Build Order Management | Sprint 5
90 | [App - Users] Test Order Management | Sprint 5
| Sprint 6 |  | 2020-11-09 | 2020-11-15
91 | [App - Users] Design Reset Password Level 2 | Sprint 6
92 | [App - Users] Build Reset Password Level 2 | Sprint 6
93 | [App - Users] Test Reset Password Level 2 | Sprint 6
94 | [App - Users] Design Inform | Sprint 6
95 | [App - Users] Build Inform | Sprint 6
96 | [App - Users] Test Inform | Sprint 6
97 | [App - Users] Design About us | Sprint 6
98 | [App - Users] Build About us | Sprint 6
99 | [App - Users] Test About us | Sprint 6
100 | [App - Users] Design Cart | Sprint 6
101 | [App - Users] Build Cart | Sprint 6
102 | [App - Users] Test Cart | Sprint 6
103 | [App - Users] Design Pay | Sprint 6
104 | [App - Users] Build Pay | Sprint 6
105 | [App - Users] Test Pay | Sprint 6
106 | [App - Users] Design Search | Sprint 6
107 | [App - Users] Build Search | Sprint 6
108 | [App - Users] Test Search | Sprint 6
| Sprint 7 |  | 2020-11-16 | 2020-11-22
109 | [App - Admin] Design Member Management | Sprint 7
110 | [App - Admin] Build Member Management | Sprint 7
111 | [App - Admin] Test Member Management | Sprint 7
112 | [App - Admin] Design Shop Management | Sprint 7
113 | [App - Admin] Build Shop Management | Sprint 7
114 | [App - Admin] Test Shop Management | Sprint 7
115 | [App - Admin] Design List Products Management | Sprint 7
116 | [App - Admin] Build List Products Management | Sprint 7
117 | [App - Admin] Test List Products Management | Sprint 7
118 | [App - Admin] Design List Customer Management | Sprint 7
119 | [App - Admin] Build List Customer Management | Sprint 7
120 | [App - Admin] Test List Customer Management | Sprint 7
121 | [App - Admin] Design Customer Notification Management | Sprint 7
122 | [App - Admin] Build Customer Notification Management | Sprint 7
123 | [App - Admin] Test Customer Notification Management | Sprint 7
124 | [App - Admin] Design Manage Customer Orders | Sprint 7
125 | [App - Admin] Build Manage Customer Orders | Sprint 7
126 | [App - Admin] Test Manage Customer Orders | Sprint 7
| Sprint 8 |  | 2020-11-23 | 2020-11-29
127 | [App - Admin] Design Messenger Mangement | Sprint 8
128 | [App - Admin] Build Messenger Mangement | Sprint 8
129 | [App - Admin] Test Messenger Mangement | Sprint 8
130 | [App - Admin] Design Payment Settings | Sprint 8
131 | [App - Admin] Build Payment Settings | Sprint 8
132 | [App - Admin] Test Payment Settings | Sprint 8
133 | [App - Admin] Design Shipping Settings | Sprint 8
134 | [App - Admin] Build Shipping Settings | Sprint 8
135 | [App - Admin] Test Shipping Settings | Sprint 8